## Sheet1
No | Process | Input | Output
1 | Develop Project Charter | 1. Project Statement of Work | 1. Project Charter
2. Business Case
3. Contract
4. Enterprise Environmental Factors
5. Organizational Process Assets
2 | Identify Stakeholders | 1. Project Charter | 1. Stakeholder Register
|  | 2. Procurement Documents | 2. Stakeholder Management Strategy
3. Enterprise Environmental Factors
4. Organizational Process Assets
3 | Develop Project Management Plan | 1. Project Charter | 1. Project Management Plan
2. Outputs from Planning Processes
3. Enterprise Environmental Factors
4. Organizational Process Assets
4 | Collect Requirements | 1. Project Charter | 1. Requirements Documentation
|  | 2. Stakeholder Register | 2. Requirements Management Plan
3. Requirements Traceability Matrix
5 | Define Scope | 1. Project Charter | 1. Project Scope Statement
|  | 2. Requirements Documentation | 2. Project Document Updates
3. Organizational Process Assets
6 | Create WBS | 1. Project Scope Statement | 1. WBS
|  | 2. Requirements Documentation | 2. WBS Dictionary
|  | 3. Organizational Process Assets | 3. Scope Baseline
4. Project Documet Updates
7 | Define Activities | 1. Scope Baseline | 1. Activity List
|  | 2. Enterprise Environmental Factors | 2. Activity Attributes
|  | 3. Organizational Process Assets | 3. Milestone List
8 | Sequence Activities | 1. Activity List | 1. Project Schedule Network Diagram
|  | 2. Activity Attributes | 2. Project Document Updates
3. Milestone List
4. Project Scope Statement
5. Organizational Process Assets
9 | Estimate Activity Resources | 1. Activity List | 1. Activity Resource Requirements
|  | 2. Activity Attributes | 2. Resource Breakdown Structure
|  | 3. Resource Calendars | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
10 | Estimate Activity Durations | 1. Activity List | 1. Activity Durations Estimate
|  | 2. Activity Attributes | 2. Project Document Updates
3. Activity Resource Requirements
4. Resource Calendars
5. Project Scope Statement
6. Enterprise Environmental Factors
7. Organizational Process Assets
11 | Develop Schedule | 1. Activity List | 1. Project Schedule
|  | 2. Activity Attributes | 2. Schedule Baseline
|  | 3. Project Schedule Network Diagram | 3. Schedule Data
|  | 4. Activity Resource Requirements | 4. Project Document Updates
5. Resource Calendars
6. Activity Duration Estimates
7. Project Scope Statement
8. Enterprise Environmental Factors
9. Organizational Process Assets
12 | Estimate Costs | 1. Scope Baseline | 1. Activity Cost Estimates
|  | 2. Project Schedule | 2. Basis of Estimates
|  | 3. Human Resource Plan | 3. Project Document Updates
4. Risk Register
5. Enterprise Environmnetal Factors
6. Organizational Process Assets
13 | Deterimine Budget | 1. Activity Cost Estimates | 1. Cost Performance Baseline
|  | 2. Basis of Estimates | 2. Project Funding Requirements
|  | 3. Scope Baseline | 3. Project Document Updates
4. Project Schedule
5. Resource Calendars
6. Contract
7. Organizational Process Assets
14 | Plan Quality | 1. Scope Baseline | 1. Quality Management Plan
|  | 2. Stakeholder Register | 2. Quality Metrics
|  | 3. Cost Performance Baseline | 3. Quality Checklist
|  | 4. Schedule Baseline | 4. Process Improvement Plan
|  | 5. Risk Register | 5. Project Document Updates
6. Enterprise Environmental Factors
7. Organizational Process Assets
15 | Develop Human Resource Plan | 1. Activity Resource Requirements | 1. Human Resource Plan
2. Enterprise Environmental Factors
3. Organizational Process Assets
16 | Plan Communications | 1. Stakeholder Register | 1. Communication Management Plan
|  | 2. Stakeholder Management Strategy | 2. Project Document Updates
3. Enterprise Environmental Factors
4. Organizational Process Assets
17 | Plan Risk Management | 1. Project Scope statement | 1. Risk Management Plan
2. Cost Management Plan
3. Schedule Management Plan
4. Communication Management Plan
5. Enterprise Environmental Factors
6. Organizational Process Assets
18 | Identify Risks | 1. Risk Management Plan | 1. Risk Register
2. Activity Cost Estimates
3. Activity Duration Estimates
4. Scope Baseline
5. Stakeholder Register
6. Cost Management Plan
7. Schedule Management Plan
8. Quality Management Plan
9. Project Documents
10. Enterprise Environmental Factors
11. Organizational Process Assets
19 | Perform Qualitative Risk Analysis | 1. Risk Register | 1. Risk Register Updates
2. Risk Management Plan
3. Project Scope Statement
4. Organizational Process Assets
20 | Perform Quantitative Risk Analysis | 1. Risk Register | 1. Risk Register Updates
2. Risk Management Plan
3. Cost Management Plan
4. Schedule Management Plan
5. Organizational Process Assets
21 | Plan Risk Responses | 1. Risk Register | 1. Risk Register Updates
|  | 2. Risk Management Plan | 2. Risk-related Contract Decisions
3. Project Management Plan Updates
4. Project Document Updates
22 | Plan Procurements | 1. Scope Baseline | 1. Procurement Management Plan
|  | 2. Requirements Documents | 2. Procurement Statement of Work
|  | 3. Teaming Agreements | 3. Make or Buy Decisions
|  | 4. Risk Register | 4. Procurement Documents
|  | 5. Risk-related Contract Decisions | 5. Source Selection Criteria
|  | 6. Activity Resource Requirements | 6. Change Requests
7. Project Schedule
8. Activity Cost Estimates
9. Cost Performance Baseline
10. Enterprise Environmental Factors
11. Organizational Process Assets
23 | Direct & Manage Project Executions | 1. Project Management Plan | 1. Deliverables
|  | 2. Approved Change Requests | 2. Work Performance Information
|  | 3. Enterprise Environmental Factors | 3. Change Requests
|  | 4. Organizational Process Assets | 4. Project Management Plan Updates
5. Project Document Updates
24 | Perform Quality Assurance | 1. Project Management Plan | 1. Organizational Process Assets Updates
|  | 2. Quality Metrics | 2. Change Requests
|  | 3. Work Performance Information | 3. Project Management Plan Updates
|  | 4. Quality Control Measurements | 4. Project Documents Updates
25 | Acquire Project Team | 1. Project Management Plan | 1. Project Staff Assignments
|  | 2. Enterprise Environmental Factors | 2. Resource Calendars
|  | 3. Organizational Process Assets | 3. Project Management Plan Updates
26 | Develop Project Team | 1. Project Staff Assignments | 1. Team Performance Assessments
|  | 2. Project Management Plan | 2. Enterprise Environmental Factors Updates
3. Resouce Calendars
27 | Manage Project Team | 1. Project Staff Assignments | 1. Enterprise Environmental Factors Updates
|  | 2. Project Management Plan | 2. Organizational Process Assets Updates
|  | 3. Team Performance Assessments | 3. Change Requests
|  | 4. Performance Reports | 4. Project Management Plan Updates
5. Organizational Process Assets
28 | Distribute Information | 1. Project Management Plan | 1. Organizational Process Assets Updates
2. Performance Reports
3. Organizational Process Assets
29 | Manage Stakeholder Expectations | 1. Stakeholder Register | 1. Organizational Process Assets Updates
|  | 2. Stakeholder Management Strategy | 2. Change Requests
|  | 3. Project Management Plan | 3. Project Management Plan Updates
|  | 4. Issue Log | 4. Project Document Updates
5. Change Log
6. Organizational Process Assets
30 | Conduct Procurements | 1. Project Management Plan | 1. Selected Sellers
|  | 2. Procurement Documents | 2. Procurement Contract Award
|  | 3. Source Selection Criteria | 3. Resource Calendars
|  | 4. Qualified Seller List | 4. Change Requests
|  | 5. Seller Proposals | 5. Project Management Plan Updates
|  | 6. Project Documents | 6. Project Document Updates
7. Make or Buy Decisions
8. Teaming Agreements
9. Organizational Process Assets
31 | Monitor & Control Project Works | 1. Project Management Plan | 1. Change Requests
|  | 2. Performance Reports | 2. Project Management Plan Updates
|  | 3. Enterprise Environmental Factors | 3. Project Document Updates
4. Organizational Process Assets
32 | Perform Integrated Change Control | 1. Project Management Plan | 1. Change Requests Status Updates
|  | 2. Work Performance Information | 2. Project Management Plan Updates
|  | 3. Change Requests | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
33 | Verify Scope | 1. Project Management Plan | 1. Accepted Deliverables
|  | 2. Requirements Documentation | 2. Change Requests
|  | 3. Requirements Traceability Matrix | 3. Project Document Updates
4. Validated Deliverables
34 | Control Scope | 1. Project Management Plan | 1. Work Performance Measurements
|  | 2. Work Performance Information | 2. Organizational Process Assets Updates
|  | 3. Requirements Documentation | 3. Change Requests
|  | 4. Requirements Traceability Matrix | 4. Project Management Plan Updates
|  | 5. Organizational Process Assets | 5. Project Document Updates
35 | Control Schedule | 1. Project Management Plan | 1. Work Performance Measurements
|  | 2. Project Schedule | 2. Organizational Process Assets Updates
|  | 3. Work Performance Information | 3. Change Requests
|  | 4. Organizational Process Assets | 4. Project Management Plan Updates
5. Project Document Updates
36 | Control Costs | 1. Project Management Plan | 1. Work Performance Measurements
|  | 2. Project Funding Requirements | 2. Budget Forecasts
|  | 3. Work Performance Information | 3. Organizational Process Assets Updates
|  | 4. Organizatonal Process Assets | 4. Change Requests
5. Project Management Plan Updates
6. Project Document Updates
37 | Perform Quality Control | 1. Project Management Plan | 1. Quality Control Measurements
|  | 2. Quality Metrics | 2. Validated Changes
|  | 3. Quality Checklist | 3. Validated Deliverables
|  | 4. Work Performance Measurements | 4. Organizational Process Assets Updates
|  | 5. Approved Change Requests | 5. Change Requests
|  | 6. Deliverables | 6. Project Management Plan Updates
|  | 7. Organizational Process Assets | 7. Project Document Updates
38 | Report Performance | 1. Project Management Plan | 1. Performance Reports
|  | 2. Work Performance Information | 2. Organizational Process Assets Updates
|  | 3. Work Performance Measurements | 3. Change Requests
4. Budget Forecasts
5. Organizational Process Assets
39 | Monitor & Control Risks | 1. Risk Register | 1. Risk Register Updates
|  | 2. Project Management Plan | 2. Organizational Process Assets Updates
|  | 3. Work Performance Information | 3. Change Requests
|  | 4. Performance Reports | 4. Project Management Plan Updates
5. Project Documents Updates
40 | Administer Procurements | 1. Procurement Documents | 1. Procurement Documentation
|  | 2. Project Management Plan | 2. Organizational Process Assets Updates
|  | 3. Contract | 3. Change Requests
|  | 4. Performance Reports | 4. Project Management Plan Updates
5. Approved Change Requests
6. Work Performace Information
41 | Close Project or Phase | 1. Project Management Plan | 1. Final Product, Service and Result Transition
|  | 2. Accepted Deliverables | 2. Organizational Process Assets Updates
3. Organizational Process Assets
42 | Close Procurements | 1. Project Management Plan | 1. Closed Procurements
|  | 2. Procurement Documents | 2. Organizational Process Assets Updates

## All Process
Process | Process Groups
Integration
Develop Project Charter | Initializing
Develop Project Management Plan | Planning
Direct and Manage Project Work | Executing
Manage Project Knowledge | Executing
Monitor and Control Project Work | Monitoring and Controlling
Perform Integrated Change Control | Monitoring and Controlling
Close Project or Phase | Closing
Scope
Plan Scope Management | Planning
Collect Requirements | Planning
Define Scope | Planning
Create WBS | Planning
Validate Scope | Monitoring and Controlling
Control Scope | Monitoring and Controlling
Schedule
Plan Schedule Management | Planning
Define Activities | Planning
Sequence Activities | Planning
Estimate Activity Durations | Planning
Develop Schedule | Planning
Control Schedule | Monitoring and Controlling
Cost
Plan Cost Management | Planning
Estimate Costs | Planning
Determine Budget | Planning
Control Costs | Monitoring and Controlling
Quality
Plan Quality Management | Planning
Manage Quality | Executing
Control Quality | Monitoring and Controlling
Resources
Plan Resource Management | Planning
Estimate Activity Resources | Planning
Acquire Resources | Executing
Develop Team | Executing
Manage Team | Executing
Communications
Plan Communications Management | Planning
Manage Communications | Executing
Monitor Communications | Monitoring and Controlling
Risk
Plan Risk Management | Planning
Identify Risks | Planning
Perform Qualitative Risk Analysis | Planning
Perform Quantitative Risk Analysis | Planning
Plan Risk Responses | Planning
Implement Risk Responses | Executing
Monitor Risks | Monitoring and Controlling
Procurement
Plan Procurement Management | Planning
Conduct Procurements | Executing
Control Procurements | Monitoring and Controlling
Stakeholders
Identify Stakeholders | Initializing
Plan Stakeholder Engagement | Planning
Manage Stakeholder Engagement | Executing
Monitor Stakeholder Engagement | Monitoring and Controlling

## Integration
Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Work | Manage Project Knowledge | Monitor and Control Project Work | Perform Integrated Change Control | Close Project or Phase

## Scope
Scope

## Resources
Re